## About
About this Management Budget Spreadsheet

This spreadsheet was created by the Trustees of the Brittany, Tokai Villas Body Corporate in
consultation with Property Principals. It is intended to assist in drawing up a maintenance plan
as required by the Sectional Title Schemes Management Act and to ensure that the Body
Corporate has sufficient reserves to fund the plan.

This spreadsheet is free software licensed under the Gnu Public License (GPL). You should have
obtained a copy of the GPL with this spreadsheet. Please read the license before using it in
any financial planning.

There is documentation for how to use this software but if you're in a hurry to just start using
the spreadsheet, the cells in grey in the next three worksheets are the ones that need to be
completed to get estimates of the financial health of a Body Corporate's finances.

© 2017 The Brittany, Tokai Villas Body Corporate

## Current Financials
Previous and Current Year Financials
This worksheet contains:
- Assumptions about inflation and the interest rate applicable to the reserve fund
- Financial data for the previous financial year
- The total administrative budget for the current year
- The projected repairs and maintenance costs for the current year

Current Financial Year	2018
Previous year administrative costs	823896
Previous year total budget	907896
Current year projected administrative costs	881569
Current year projected repairs and maintenance costs	165000
Current year initial reserve fund amount	570000
Assumed inflation rate	7.00%
Bank deposit interest rate	5.00%

## Ten Year Plan
Ten Year Plan
This spreadsheet contains items that need to be budgeted for over the next 10 years.
Budgeted items would include:
- Repainting
- Security enhancements
- Wall and fence repairs and replacement
- Gutter and drainpipe repairs and replacment

It is possible to specify a range of years over which maintenance work must be done.
For example, it might be that gutters will be replaced over two years. It is also possible to
specify that some maintenance work must be done every N years; e.g. that woodwork
repainting happens every 4 years.

Item	Start Year	End Year	Step (years)	Annual amount (real)		2018	2019	2020	2021	2022	2023	2024	2025	2026	2027
Repainting woodwork	2018	2018	1	270000		270000	0	0	0	0	0	0	0	0	0
Repainting walls	2021	2021	1	710000		0	0	0	869781	0	0	0	0	0	0
Repainting woodwork	2023	2023	1	240000		0	0	0	0	0	336612	0	0	0	0
TV Upgrade	2020	2020	1	100000		0	0	114490	0	0	0	0	0	0	0
Water-wise plants	2018	2027	1	5000		5000	5350	5725	6125	6554	7013	7504	8029	8591	9192
Replacing irrigation system	2025	2025	1	80000		0	0	0	0	0	0	0	128463	0	0
Gutters and downpipes	2020	2021	1	125000		0	0	143113	153130	0	0	0	0	0	0
Fibre-optic installation	2021	2021	1	500000		0	0	0	612522	0	0	0	0	0	0
Individual water meters	2023	2023	1	300000		0	0	0	0	0	420766	0	0	0	0
Improved vlei lighting	2019	2019	1	20000		0	21400	0	0	0	0	0	0	0	0
Solar initiative	2024	2024	1	50000		0	0	0	0	0	0	75037	0	0	0
Electric fence	2027	2027	1	25000		0	0	0	0	0	0	0	0	0	45961
CCTV cameras	2019	2023	2	25000		0	26750	0	30626	0	35064	0	0	0	0
Water tanks	2019	2021	2	6000		0	6420	0	7350	0	0	0	0	0	0
ClearVu fence	2024	2024	1	160000		0	0	0	0	0	0	240117	0	0	0
Driveway	2018	2027	1	0		0	0	0	0	0	0	0	0	0	0
Pipes	2027	2027	1	0		0	0	0	0	0	0	0	0	0	0
Roofs	2018	2027	1	0		0	0	0	0	0	0	0	0	0	0
Boundary walls	2018	2027	1	0		0	0	0	0	0	0	0	0	0	0
Pool	2024	2024	1	48000		0	0	0	0	0	0	72035	0	0	0
Replace gate	2027	2027	1	0		0	0	0	0	0	0	0	0	0	0

## Planning and Projections
Planning and Projections

Year	2018	2019	2020	2021	2022	2023	2024	2025	2026	2027
Proposed budget change real (%)	14.00%	14.00%	14.00%	0.00%	0.00%	0.00%	0.00%	0.00%	0.00%	0.00%
Proposed budget change nominal (%)	21.00%	21.00%	21.00%	7.00%	7.00%	7.00%	7.00%	7.00%	7.00%	7.00%
Initial reserve (nominal)	570000	537584	906818	1304705	279501	1006781	988293	1447823	2259157	3307113
Administrative budget (nominal)	881569	943279	1009308	1079960	1155557	1236446	1322997	1415607	1514700	1620729
Repairs & Maintenance (nominal)	165000	176550	188909	202132	216281	231421	247621	264954	283501	303346
Total budget (nominal)	1098554	1329251	1608393	1720981	1841449	1970351	2108275	2255855	2413764	2582728
Management budget (nominal)	216985	385972	599085	641021	685892	733905	785278	840247	899065	961999
Management budget OK?
Management spend (nominal)	275000	59920	263327	1679534	6554	799454	394692	136491	8591	55154
Final reserve (nominal)	537584	906818	1304705	279501	1006781	988293	1447823	2259157	3307113	4424656
Final reserve (months)	7.3	11.5	15.5	3.1	10.5	9.6	13.1	19.2	26.2	32.8
Final reserve OK?

## Budget Summary
Budget Summary

Total budget	1098554
Reserves at the start of the year	570000
Anticipated reserves at year end	537584
Percentage change in reserves	-5.7%
Equivalent reserves in months	7.3